## Slide 1: City of Nanaimo Core Services Review Council Steering Committee Workshop #2
March 7, 2016

## Slide 2: Objectives
To review project progress to date
To discuss observations and themes

## Slide 3: Progress to date

## Slide 4: Off to a good start
Good cooperation from participants
Management and staff engaged
Departments providing requested information on a timely basis
Initial council workshop gave good direction and focus

## Slide 5: Services/Processes To Be Reviewed
Sixteen services were selected
Six corporate-wide processes

## Slide 6: In-Scope Service Areas Reviewed
HR Recruitment/Retention/Success Planning/Training
  Percentage Complete: 50%
HR/Compensation
    Percentage Complete: 35%
Financial Policies
    Percentage Complete: 30%
Transportation (Operations)
    Percentage Complete: 15%
Sanitation
    Percentage Complete: 50%
Notes: ONE SENTENCE FOR EACH

## Slide 7: In-Scope Service Areas Reviewed
Fleet Services
    Percentage Complete: 50%
Police Support
    Percentage Complete: 40%
Bylaw/Parking
    Percentage Complete: 50%
Facilities Planning and Operations
    Percentage Complete: 50%
Recreation Administration, Operations and Environment
    Percentage Complete: 60%

## Slide 8: In-Scope Service Areas Reviewed
Permissive Tax Exemptions and Grants
    Percentage Complete: 80%
Nanaimo Economic Development Corporation
    Percentage Complete: 45%
Downtown Nanaimo Business Improvement Association
    Percentage Complete: 80%
Building Permits and Inspections
    Percentage Complete: 60%
Subdivision, Development, Land Use Planning and Approvals
    Percentage Complete: 60%
Vancouver Island Conference Centre
    Percentage Complete: 10%

## Slide 9: Corporate-Wide Processes Reviewed
Strategic planning, business planning and budgeting
    Percentage Complete: 30%
Capital projects planning and development
    Percentage Complete: 25%
Asset management
    Percentage Complete: 30%
Project Management
    Percentage Complete: 10%
Purchasing and contract administration
    Percentage Complete: 60%
Performance Measurement
    Percentage Complete: 10%

## Slide 10: Interviews Completed
Mayor and Council
City Manager
Directors
Managers
Union leaders
Focus Groups and individual staff members

## Slide 11: Documents Reviewed
Policies
Financial statements
Fee Structures
Service Standards
Most departments prepared information binders for our arrival
Collective agreement

## Slide 12: Staff Survey
Management: 84% participation rate
Staff: 52% participation rate

## Slide 13: Benchmarking and Best Practices Research
Where appropriate, benchmarks are being sought from other cities
  Prince George
  Port Coquitlam
  Kelowna
  Kamloops
  North Vancouver
  Chilliwack
Best practices are sought on a service by service basis
  Calgary, Ottawa, Winnipeg, Edmonton, Toronto, Windsor, London, Saanich, Delta and others

## Slide 14: Initial observations

## Slide 15: Organizational Health and Competence
Generally co-operative, competent and committed management and staff – many suggestions for improvements
Considerable strengths in most areas
  In some cases, Nanaimo is a leading practice place
Roles, expectations and relationships among city and external agencies are poorly articulated
Service levels and goals are not defined
Staff focus is on customer satisfaction and activity completion, less on cost savings

## Slide 16: Organizational Health and Competence
Information lacking on outcomes and customer service requirements in some areas
Staff and managers feel efforts under-appreciated by Council and the public
Some staff feel management fail to value their experience
Communications throughout the organization could be improved

## Slide 17: Operations and Management
Many managers focused on day to day operations with little time for planning
State of art information systems not fully used in some cases to guide management decisions
In other cases, there is need for modern information systems to support operations and management
Fleet and equipment often kept beyond economic life

## Slide 18: Next Steps
Continue research and analysis
Identify and assess opportunities for improvement and implications for change
Preparation for April presentation to Steering Committee